## Sheet1
The information contained here is provided by Partners in Medical Education, Inc. (Partners®) ‘as is’ for educational and informational purposes only.
www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com
|  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Program Level Administration
Complete Program Reports for GMEC | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jul to www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
AMA Frieda updated | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Aug
Milestone Reporting - ACGME upload | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Dec; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Update program web page | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jan
Review program budget | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Nov
Conduct Program Annual Evaluation | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Apr
Review & update evals for next academic year (NAY) | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Mar
Finalize & confirm evals for NAY | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Mar
Program Manual finalized for NAY | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Apr
Resident Evaluations Core Faculty | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Dec; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Needs Assessment for Faculty Development | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com May
Program Director Evalutes Core Faculty | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Name Program Evaluation Committee | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Dec
Conduct Annual Program Evalution | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Apr
Update ADS | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Aug
Update Opportunities (AOA) | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com May
TIVRA | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Prepare Resident Final Verifications | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Ensure graduate evaluations and reports complete | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Curriculum
Review draft rotation schedule for NAY | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jan
Review & update curriculum | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Feb
Finalize rotation schedule | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Apr
Rotation Confirmations sent to preceptors | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Apr
Review & confirm rotations for NAY | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Apr
Confirm preceptor continuity schedule (contracts) | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Apr
Start didactic schedule for NAY | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Mar
Confirm didactic schedule | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com May
Current residents
Monitor Duty Hour - rotation, shifts, call & service changes | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jul to www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Review rotation evaluations | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jul to www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Review resident scholarly activity | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jul; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Dec; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Quarterly evaluations due | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Sep; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Dec; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Mar; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Review quarterly eval w/ resident | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Oct; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jan; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Apr
Annual Resident Review (AOA) | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Clinical Competency Committee meets | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Sep; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Dec; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Mar
Semi-annual evaluation | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Dec; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Resident promotion decision | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Mar
Prepare Graduation Certificates | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Apr
Graduation Ceremony | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
In-service exams - classrooms booked | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Aug; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Nov
Recruiting
Register for NRMP & NMS | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Aug
Review ERAS apps & offer interviews | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Sep to www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Oct
Interviews | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Oct to www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jan
| Finalize, submit rank list | www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jan: AOA; www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Feb: ACGME
| Scramble | www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Feb: AOA
Draft / review orientation schedule | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Feb
Finalize & confirm orientation schedule | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Apr
Plan for program specific orientation | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com May
Orientation - general, specific, picnic | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Jun
Register for ERAS | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Apr
Set interview dates for next season | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Mar
Review & confirm # positions for next year match | bar: www.PartnersInMedEd.com 724-864-7320 Info@PartnersInMedEd.com Apr