## High - Level Roadmap
|  |  |  | 20-- | 20-- | 20-- | 20-- | 20-- | 20-- | 20-- | 20-- | 20-- | 20-- | 20-- | 20-- | 20-- | 20-- | 20--
|  |  |  | Jan - Mar | Apr-Jun | Jul-Sep | Oct - Dec | Jan - Mar | Apr-Jun | Jul-Sep | Oct - Dec | Jan - Mar | Apr-Jun | Jul-Sep | Oct - Dec | Jan - Mar | Apr-Jun | Jul-Sep
Develop Project Charter |  |  | Determine scope, guiding principles and objectives
Develop project structure (steering committee?)
Define success measures
Develop High Level Project Plan/Road Map and Time Lines
Mobilize workstreams
Monitor project status and progress
Workstreams | Lead | Status
Pysical Resources |  |  | Determine space needs for programs (outpatient, OR, inpatient)
Investigate consulting company for assistance with facility development
Create list of required specialty-specific spaces (e.g. Sugery will need a sim center)
Create list of required rotations that might not be able to be met at Sponsoring Institution (e.g. Surgery requires a transplant rotation)
PR/Communications |  |  | Meet with PR/Communications team
Brochure development for initial recruitment season
Website development for initial recruitment season (needs to "go live" approx 6 months prior to start of recruitment)
YouTube video about the mission and vision of NGHS to go along with brochures and website for initial recruitment season
Personnel |  |  | Hire DIO
Hire GME Director
Hire GME staff
Finance/Budget |  |  | ACGME fees
Resident salaries/benefits
Discuss book/educational fund
Purchase of any specific electronic equipment for resident use (laptops, tablets, pagers)
Human Resources |  |  | Salary and benefits for initial programs
Determine salary for trainees
Benefits (malpractice ins, health ins, wellness package)
Draft contract
Issues related to residents as hospital employees
Draft Housestaff GME Handbook (GME specific policy and procedure that is not covered in other HR documents)
IT/EMR |  |  | Determine long IT/EMR needs for residency programs
Evaluate current medical library facilities and determine if they will need to be enhanced
Create mechanism to track error reporting/near miss reporting by residents
Create mechanims for residents to report issues of concern anonymously to GME (button on physician portal, anonymous email)

## Program Timeline
20__ | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
SI | Submit SI Application |  |  | IRC Meeting
GS |  | Recruit PD |  |  | Submit Application
FCM |  |  |  |  | Recruit PD |  | Submit Application
IM | [6 empty] | Recruit PD |  |  | Submit Application
2018 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
SI
GS |  |  |  |  | Need GS Approval to Recruit |  |  |  | Recruit for GS
FCM |  |  |  |  | Need FCM Approval to Recruit |  |  |  | Recruit for FCM
IM |  |  |  |  | Need IM Approval to Recruit |  |  |  | Recruit for IM
EM | [5 empty] | Recruit PD |  | Submit Application
TY | [5 empty] | Recruit PD |  | Submit Application
20__ | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
SI |  |  |  | SI Site Visit
GS | [5 empty] | GS Start
FCM | [5 empty] | FCM Start
IM | [5 empty] | IM Start
EM |  |  |  |  | Need EM Approval to Recruit |  |  |  | Recruit for EM
TY |  |  |  |  | Need TY Approval to Recruit |  |  |  | Recruit for TY
20__ | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
EM | [5 empty] | EM Start
TY | [5 empty] | TY Start

## Documents & Activities for SV
Doucments that will be requested at Sponsoring Institution site visit | Person(s) Responsible | Follow-up
Organizational Chart 1, Position of GMEC
Organizational Chart 2, Position of DIO
Statement of Commitment to Graduate Medical Education from Governing Body
GMEC Membership List (use the ACGME template for this)
GMEC Minutes (annotated, the most recent year)
Annual Institutional Review (AIR) Executive Summaries to the Governing Body
GMEC Special Review Protocol, and Special Review Reports (if applicable)
Documentation of accreditation for patient care for all participating hospitals
An annotated copy of the residents' agreement of appointment/contract, including any additional reference material from the resident handbook or manual, with the required 12 items highlighted
Evidence residents/fellows are provided with professional liability coverage
POLICIES
Policies and procedures on resident eligibility and selection
Institutional policy(ies) not necessarily GME-specific, covering sexual and other forms of harassment
Institutional policy(ies), not necessarily GME-specific, regarding accommodations for disabilities consistent with all applicable laws and regulations.
Institutional policy(ies), not necessarily GME-specific, that addresses physician impairment
Institutional policy(ies) for effective oversight of level compliance with ACGME work hour standards
Institutional policy(ies) for supervision of residents/fellows
Institutional policy(ies) regarding the criteria for promotion and/or renewal of a resident's/fellow's appointment
Institutional policy(ies) addressing resident/fellow due process relating to actions of suspension, non-renewal, non-promotion, or dismissal
Institutional policy(ies) for submitting and processing resident/fellow grievances at the program and institutional levels
Institutional policy(ies) for vacation and other leaves of absence
Institutional policy(ies) on moonlighting, including provisions that residents/fellows are not required to engage in moonlighting
Policy that addresses interactions between vendor representatives/corporations and residents/fellows and accredited programs
Policy prohibiting the sponsoring institution or any of its accredited programs from requiring a resident/fellow to sign a non-competition guarantee or restrictive covenant
Policy addressing administrative support for accredited programs and residents/fellows in the event of a disaster or interruption in patient care